## Risk Register
No. | Rank | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 1 | Similar platform lunched earlier than our platform. | Market risk | Another company has announced a similar platform | The competitor releases the platform | Use more advertisement, or implementing more features. | Project manager | High | High | The risk event did not occur yet
R2 | 2 | Schedule estimation is far less than the actual one. | Time risk | schedule cereator are inexperienced | uncarefully schedule approval | Get an expert to update the schedule to more realistic one. | Project Manager | Medium | Medium at the beginning, gets higher with time | The risk event did not occur yet
R4 | 3 | delayed in budget spends because bureaucracy of the finance department. | Financial risk | Unapproved by financial department | Financial difficulties like lack of investment | We may adjust the budget and lower it or convince investors with potential project revenue. | Project manager | Medium | High | The risk event did not occur
R5 | 4 | Important employee may leave the company | People Risk | employee's family is in other city | Family issues | Employing another person with a similier set of skills. | Project Manager | High | Medium | The PM will meet with the employee
R3 | 5 | Technical diffculties such as acculmative bugs or bad design | Technical risk | Inexprienced staff or trying new technology | Aquiring new technlogy or bad recuritment | Applying recoverability mesaures to recover stable sub systems and enlisting the help of senior technical staff | Project manager | Low | Medium | The risk event did not occur